## Sheet1
Test Date | Milestone / Release | Tester
2025-05-23 |  | MN/ PH
Test Scenario | Regression testing post EdWeb Release
Test Case | Full regression testing of Staging environment
Pre-Conditions | https://wpp-sso-sandbox.is.ed.ac.uk/
New Site Install
Test Steps # | Test Step Details | Actual Outcome | Result
1 | Admin can login to the CMS |  | pass | MN
2 | Admin can create new users for each role |  | pass
3 | Create Parent group |  | pass
| Default email should be set to "edweb-no-reply@ed.ac.uk" |  | pass
| Site wide banner can be loaded |  | pass
| Site wide banner logo can be loaded |  | pass
| Site-wide colour theme can be updated |  | pass
| Minor banner heading displays as expected |  | pass
| Top level navigation can be enabled / disabled |  | pass
| Beta message can be enabled / disabled |  | pass
| Contact button can be added |  | pass
| Subsite footers can be added |  | pass
| Subsite footer images can be added - with & without link |  | pass
| Parent Page homepage can be saved |  | pass
4 | Add a User to Group |  | pass
5 | Parent Page homepage can be edited |  | pass
| Parent Page homepage can be saved |  | pass
6 | Basic Site sittings (admin/config/system/site-information) |  | pass
| Site Name updated |  | pass
| Default email should be set to "edweb-no-reply@ed.ac.uk" |  | pass
7 | WPP Group settings can be set (admin/config/wpp_group/settings) |  | pass
User Access
Ticket # | Test Step Details | Actual Outcome | Result
Site Editor
Add page types (Overview, Event, Generic Content, Landing Page, News)
Cannot publish / unpublish content - move between Draft and In Review
Can add paragraphs
CK Editor restricted to UoE text format
Add page to menu
| cannot delete content (only Admin/ SIte Owners can delete) | delete button still present
| Publisher | tested with site editor
| As above for editor (needs to have this permission added also) | (Event, Generic Content, Landing Page, News)
Page change can be saved
Page can be published
Page can be unpublished
| Site Owner | tested with publisher + site editor
As above for publisher (needs to have this permission added also)
Can create homepage
Can add new users
| WebForm User | tested with publisher + site editor
Access to add and edit webforms
| Site Architect | tested with site editor
Access to create content types (/admin/structure/types/add)
Page Creation
Ticket # | Test Step Details | Actual Outcome | Result
Homepage
Can only be added by site owner and above
Parent Page homepage page content - layout can be added
Feature row
Paragraphs can be added - Body text - Button - Card - Custom HTML - Document - Feature box - Heading - Image - Link - Quote - Video - Media Hopper video - Paragraph container - Two column - Webform - Custom HTML card - video card
Generic Content Page
Can be added by site editor
Paragraphs can be added - Accordion - Body text - Button - Contact - Custom HTML - Document - Feature box - From Library - Heading - Image - image gallery - Link - Media Hopper Video - Paragraph Container - profile listing - Quote - Related Content - Table - Two Column - Video - WebForm - add listing -add layout section
Summary Shows on page
can add to menu
can change alias
Landing Page
can be added by site editor
Paragraphs can be added - Accordion - Body text - Button - Card - Contact - Custom HTML - Document - Event card - Feature box - From Library - Heading - Image - Layout - Link - Media Hopper Video - Paragraph Container - Quote - Related Content - Table - Two Column - Video - WebForm - listing - custom HTML - profile listing - video card
summary shows
Can add compontent to page content area
additional page content shows
Subsection overview content shows
dynamic cards show
| Subsection overview content config works | taking this to mean the toolbar and text dropdown [PH]
can add to menu
can change alias
| News Article |  |  | PH
can be added by site editor
Paragraphs can be added - Body text - Button - Contact - Document - Feature box - From Library - Heading - Image - Link - Media Hopper Video - Quote - Related Content - Table - Two Column - Video - WebForm - image gallery - paragraph container -add layout section
| can add to menu |  | pass
can change alias
Event
can be added by site editor
Paragraphs can be added - Body text - Button - Contact - Feature box - From Library - Heading - Image - Link - Media Hopper Video - Link - Quote - Related Content - Table - Two Column - Video - WebForm -add layout section
can add to menu
can change alias
Media
Ticket # | Test Step Details | Actual Outcome | Result
Can upload contact card
Can upload documents 5 MB limit. Allowed types: txt rtf doc docx ppt pptx xls xlsx pdf odf odg odp ods odt fodt fods fodp fodg key numbers pages.
Custom HTML field
Can upload image 1 MB limit. Allowed types: png gif jpg jpeg.
Can add link
Can add remote video
Can add streaming media
Can add video
General
Ticket # | Test Step Details | Actual Outcome | Result
Left hand navigation functions and is styled correctly
Assets
Ticket # | Test Step Details | Actual Outcome | Result
Edit view
LHC toolbar available
Correct menu items for user group
Editing Tools
can view latest version
can access Revisions
Within Revisions
can revert to a previous revision
can unpublish page
can republish page
can access and compare revisions on different tabs
CK Editor
| Styling and Formating working as expected (If testing with Admin - make sure other roles are unticked) | multiple editor versions avialble to editor/publisher UoE text format - UoE custom html format
General page editing
mandatory fields
move page within menu
remove page from menu
Ailias can be edited
Edit can be saved
Edit can be published
Redriects
can be created
can be removed
User permissions
can be added
can be removed
R202505-01 | https://gitlab.com/wpp1/uoe-webcore/-/issues/239 | Pass - see updated comments on gitlab ticket | PH
| https://gitlab.com/wpp1/uoe-webcore/-/issues/233 | query - CLP heroes not converting but Billy may pass as per FBs | PH
| https://gitlab.com/wpp1/uoe-webcore/-/issues/232 |  | PH
| https://gitlab.com/wpp1/uoe-webcore/-/issues/228 |  | PH
| https://gitlab.com/wpp1/uoe-webcore/-/issues/226 |  | PH
| https://gitlab.com/wpp1/uoe-webcore/-/issues/224 |  | MN
| https://gitlab.com/wpp1/uoe-webcore/-/issues/223 | Pass - see updated comments on gitlab ticket | MN | Pass
| https://gitlab.com/wpp1/uoe-webcore/-/issues/212 | Pass - see updated comments on gitlab ticket | MN | Pass
| https://gitlab.com/wpp1/uoe-webcore/-/issues/211 | Pass - see updated comments on gitlab ticket | MN | Pass
| https://gitlab.com/wpp1/uoe-webcore/-/issues/210 | Pass - see updated comments on gitlab ticket | MN | Pass
| https://gitlab.com/wpp1/uoe-webcore/-/issues/205 | Pass - see updated comments on gitlab ticket | MN | Pass
R202505-02 | https://gitlab.com/wpp1/uoe-webcore/-/issues/237
https://gitlab.com/wpp1/uoe-webcore/-/issues/202
| https://gitlab.com/wpp1/uoe-webcore/-/issues/198 |  | MN/PH
https://gitlab.com/wpp1/uoe-webcore/-/issues/248
https://gitlab.com/wpp1/uoe-webcore/-/issues/241